Organizing and Hosting An All Candidates Meeting

Sample Workplan

| Task | Details | Who | By When |
| --- | --- | --- | --- |
| Planning the All Candidates Meeting |  |  |  |
| Form a Work Group | -Small number to start, can build if desired, but smaller number is easier to work with -Key roles: coordinator(s), recorder, communication coordinator, candidate coordinator | Person with the idea | Several months before election |
| Create a Workplan | -Group brainstorms key steps or uses Guide to identify steps -Note known details -Identify person responsible -Set deadline for task completion -Update workplan as planning progresses- | Work Group | 1-2nd week |
| Set Date and Location | -Each depends on other; choose times that work around key organizers -Book well in advance to get best location -Choose location in voters’ immediate area -Choose venue that is accessible (walking, biking, bus, parking, wheelchair accessible, etc.) | Work Group Member | ASAP |
| Recruit Volunteers | Prior to Event: -logistics coordinator -moderator -technical support For event: -timekeeper -question collator -question collector -greeters -set up/clean up | Work Group | 2-3 months prior to event 1 month prior to event |
| Connect with Community | -Send out “hold-the-date” message ASAP to community and candidates -Solicit questions about key issues -Collate, debate, and refine questions -Send 3-4 questions to candidates before event -Save 3-4 questions for event | Work Group | ASAP 2-3 months prior to event |
| Task | Details | Who | By When |
| Planning the All Candidates Meeting cont’d |  |  |  |
| Connect with Candidates | -Ideally as they announce their candidacy -Complete Declaration of Sponsor for All Candidates Debate -Send invite early; send reminders if needed; include date, time, location, why participate -Send detailed follow up note with date, time, location, meeting format, expectations, etc. | Candidate Coordinator | ASAP 1 week prior |
| Collect Resources Needed | -Brainstorm a list of resources needed, depending on how you plan to run your meeting and who you think will attend -Which resources can you get donated? Can you find businesses or groups that will sponsor you? Do you need to fundraise? -Some items you may need include: -services: translation, childcare printing? -AV/Sound equipment -tables, chairs, flip chart stand, paper, markers -informational material (from candidates and others) -signage, name tags, paper, pencils -stopwatch, timer -refreshments (coffee, tea, water jugs, cups, fruit, other?) | Work Group Fundraiser? Logistics Coordinator | ASAP ASAP 1 months prior I week prior 1-2 days prior |
| Promotion | -create posters/flyers, hard/digital forms -Arrange for printing -create hard copy/digital mailing lists -send to community groups, libraries, schools, etc. via email, partner organizations, social media -post in voting area libraries, stores, parks, trails, partners’ lobbies, etc. -send to local radio, newspapers, etc. -send press release and request interviews with local news outlets | Communications Coordinator | ASAP 1 month prior and weeks leading to event 3 weeks prior |

| Task | Details | Who | By When |
| --- | --- | --- | --- |
| Develop Meeting Format | -Decide on formal or informal meeting -formal – more structured, easier to manage -informal – more participatory but risk of long-winded candidates and dominant speakers -number of candidates determines timing for each one | Work Group | 2 months prior |
| Hosting the All Candidates Meeting |  |  |  |
| Task | Details | Who | By When |
| Prior to Event | -call location to confirm all resources supplied by them are in place -send email to confirm volunteers -confirm all resources are in place | Logistics Coordinator | 1 week prior |
| Set Up | -tables, chairs -event signage on entry door and directional signage in hallways -AV/sound equipment, mics -sign-in table, table for timekeeper (stopwatch and bell) and question collator (basket for questions) -tables for candidates displays literature -candidates table with mics, jugs of water and glasses, pens/pads, signage |  | 1 hour before event |
| Greet Candidates | -greet candidates when they arrive -show them the table reserved for each of their displays/literature -show them where they are seated at the candidates table; point out water, mics, pens and note pads -answer any questions | Candidate Coordinator | At event |
| Greet Participants | -greet participants as they arrive, direct them to sign-in table -at sign-in table, ask people to record their name and email for future messaging, group they represent -provide pencil and small pieces of paper to record questions | Greeters | At event |
| Welcome/Introductions | -welcome participants and candidates -review logistics (e.g., bathrooms, refreshments, safety procedures)format, expectations and consequences for conduct -request donations for expenses, if desired | MC | At event |
| Land Acknowledgement | -see Guide for sample or use your own -make sure you know whose lands on which you are located and pronounce the names correctly | MC | At event |
| Brief Intro to Municipal Government | -what local government does -positions being elected -why it’s important to know your candidates and make an informed choice | MC | At event |
| Candidate Introductions | -candidates introduce themselves and their platforms | MC | At event |
| Prepared Questions | -use prepared questions -rotate order of responses | MC | At event |
| Questions from the Floor | -collect written questions throughout -collator condenses and refines -if time, candidates respond to questions read by MC | Question collector Question Collator MC | At event |
| Concluding Remarks | -each candidate shares final remarks | MC | At event |
| Closure | -thank candidates, audience, volunteers, and any sponsors -summary comments about success of event -invite everyone to mix and mingle for 30 minutes -ask for help with clean up, as able -remind everyone to get out and vote | MC | At event |
| Mix and Mingle | -participants stay to ask candidates questions -volunteers start cleaning up, as appropriate | Volunteers | At event |
| Clean up | -put away AV/Sound equipment and return -put away tables and chairs, as necessary -take down signage -clean up refreshments, give away what’s left -leave space as you found it -return everything used and/or borrowed | All | After event |
| Follow up | -send thank you messages to everyone: candidates, volunteers, media, any sponsors -send evaluations to candidates and sponsors: what worked, what didn’t, ideas for next time | Work Group | Within a week after |
| Debrief and Celebrate | -organize a celebration and debriefing with key organizers and volunteers -review evaluations and discuss: make recommendations for next time | Work Group | Within 2-3 weeks after |